## Test Plan
Please click here to see the complete Test plan

## TestScenarios
Project Name | StarTech
Reference Document | FRS
Created By | Tanjina Rahman
Creation Date
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Register" functionality | P0 | 29
TS_003 |  | Validate the working of the "Login" functionality. | P0 | 19
TS_005 |  | Validate the working of "Add to cart" functionality. | P1 | 11
TS_005 |  | Validate the working of " Shopping Cart" functionality. | P1 | 16
TS_015 |  | Validate the working of "Forget Password" functionality. | P2 | 9
TS_013 |  | Validate the working of "Menu Bar" functionality. | P2 | 13
TS_010 |  | Validate the working of "Search Bar" functionality. | P3 | 15
TS_009 |  | Validate the working of "Logout" functionality. | P4 | 4
TS_012 |  | Validate the working of "Header" functionality. | P5 | 11
TS_016 |  | Validate the working of "Footer" functionality. | P6 | 13
TS_014 |  | Validate the working of "OTP" functionality. | P0 | 4

## TestCase
Product Name |  | StarTech | TC Start Date |  | TC Execution Start Date | [5 empty] | TEST CASE
Module Name |  | User Management, Homepage, Add to Cart, Shopping Cart | TC End Date |  | TC Execution End Date | [5 empty] | PASS | 133
Epic |  |  | Test Case Developed By | Tanjina Rahman | Browser (tested) | Yes |  |  |  |  | FAIL | 8
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 141
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Analyzing the website using multiple browsers | Should be run in different browsers | Found as per expectation. | Chrome Microsoft Edge Firefox | 1. Visit multiple browsers 2. Search 'StarTech' 3. Visit the website |  |  | Passed
2 | User Management | UI Testing | Register | Verifying mistakes in grammar or spelling | Mistakes in grammar or spelling shouldn't be found | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying the fields' alignment | Should be as per the requirement | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Check the alignment |  |  | Passed
5 |  |  |  | Verifying by hovering over the fields | A text should appear over the fields or the color should change | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Hover over button and every fields |  |  | Passed
6 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Check red asterisk beside mandatory field |  |  | Passed
7 |  |  |  | Verifying that all buttons are clickable | All buttons should be clickable | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Click all the button |  |  | Passed
8 |  | Functional Testing |  | Verifying that mandatory fields are blank | Sholud not allow user to register and pop an error message | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Keep mandatory fields blank |  |  | Passed
9 |  |  |  | Verifying case insensitivity of firstname and lastname field | Should accept the provided input | Found as per expectation. | tAnjINa raHmaN | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input tAnjINa and raHmaN in firstname and lastname field |  |  | Passed
10 |  |  |  | Verifying by inputing numeric value in firstname and lastname field | Should not accept the provided input | Not Found as per expectation | 639178 380248 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input 639178 and 380248 in firstname and lastname field | Numeric Value Error |  | Failed
11 |  |  |  | Verifying by inputing special character in firstname and lastname field | Should not accept the provided input | Not Found as per expectation | #!!*$ &#$!! | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input #!!*$ and &#$!! in firstname and lastname field | Special Character Error |  | Failed
12 |  |  |  | Verifying by inputing valid email | Should accept the provided input | Found as per expectation. | rahmantanjina983@gmail.com | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input rahmantanjina983@gmail.com in email field |  |  | Passed
13 |  |  |  | Verifying by inputing invalid email | Shouldn't accept the invalid email and display an error message | Not Found as per expectation | jitdnj@ghv.ezs | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input jitdnj@ghv.ezs in email field | Invalid Email Error |  | Failed
14 |  |  |  | Verifying a email without domain | Shouldn't accept the email and display an error message | Found as per expectation. | fsrd&hfd.chgc | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input fsrd&hfd.chgc in email field |  |  | Passed
15 |  |  |  | Validating an email id can only be used one time | Shouldn't accept the provided input and display error | Found as per expectation. | rahmantanjina983@gmail.com | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input rahmantanjina983@gmail.com in email field |  |  | Passed
16 |  |  |  | Verifying by inputing valid phone number | Should accept the provided input | Found as per expectation. | 01813816794 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input 01813816794 in phone number field |  |  | Passed
17 |  |  |  | Verifying by inputing invalid phone number | Shouldn't accept the invalid phone number and display an error message | Found as per expectation. | 18b9310032795 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input 18b9310032795 in phone number field |  |  | Passed
18 |  |  |  | Validating an phone number can only be used one time | Shouldn't accept the provided input and display error | Found as per expectation. | 01813816794 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input 01813816794 in phone number field |  |  | Passed
19 |  |  |  | Verifying OTP code is sent successfully or not | Should send OTP code | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button |  |  | Passed
20 |  |  |  | Verifying that correct OTP is generated | Should accept the provided input | Found as per expectation. | 8863 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input 8863 in OTP code field |  |  | Passed
21 |  |  |  | Verifying that an error message should be shown in case user inputs an invalid OTP code | Shouldn't accept the provided input and display error | Found as per expectation. | 8H6s | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input 8H6s in OTP code field |  |  | Passed
22 |  |  |  | Verifying OTP code should be valid only for one time | Shouldn't accept the provided input and display error | Found as per expectation. | 8863 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input 8863 in OTP code field |  |  | Passed
23 |  |  |  | Verifying password and confirm field values are in encrypted form | Should be in encrypted form | Found as per expectation. | Password: 1234 Confirm Password: 1234 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input 1234 in password and confirm password field |  |  | Passed
24 |  |  |  | Verifying smaller password length than required | Shouldn't accept the provided input and display error | Found as per expectation. | Password: abc Confirm Password: abc | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input abc in password and confirm password field |  |  | Passed
25 |  |  |  | Verifying larger password length than required | Shouldn't accept the provided input and display error | Found as per expectation. | Password: asdfghjklpoiuytrewqzxcvbnm Confirm Password: asdfghjklpoiuytrewqzxcvbnm | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input asdfghjklpoiuytrewqzxcvbnm in password and confirm password field |  |  | Passed
26 |  |  |  | Verifying different data for password and confirm password | Shouldn't accept the provided input and display error | Found as per expectation. | Password: a1s2d3f4 Confirm Password: a1s2d3fg | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input a1s2d3f4 in password and a1s2d3fg in confirm password field |  |  | Passed
27 |  |  |  | Verifying password and confirm password field with valid length and same data | Should accept the provided input | Found as per expectation. | Password: a1s2d3f4 Confirm Password: a1s2d3f4 | "1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Fill up firstname, lastname, email and phone number with valid credentials and click 'Continue' button 4. Input a1s2d3f4 in password and confirm password field" |  |  | Passed
28 |  | Usability Testing |  | Verifying copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | Rahman | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Copy and paste Rahman in lastname field |  |  | Passed
29 |  |  |  | Verifying keyboard tab button functionality | Should switch to another field | Functioning successfully | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Click tab in every field |  |  | Passed
30 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Click enter in every field |  |  | Passed
31 |  | UI Testing | Login | Verifying mistakes in grammar or spelling | Mistakes in grammar or spelling shouldn't be found | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
32 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check the font, text color and style |  |  | Passed
33 |  |  |  | Verifying the fields' alignment | Should be as per the requirement | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check the alignment |  |  | Passed
34 |  |  |  | Verifying by hovering over the fields | A text should appear over the fields or the color should change | Found as per expectation. | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Hover over button and every fields |  |  | Passed
35 |  |  |  | Verifying that all buttons are clickable | All buttons should be clickable | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click all the button |  |  | Passed
36 |  |  |  | Verifying whether an eye icon is added to the password field or not | An eye icon should be available in password field | Not found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check that eye icon is available or not in password field | Eyeicon Error |  | Failed
37 |  |  |  | Verifying that there is a 'Remember me' checkbox on the login page | A 'Remember me' checkbox should be available | Not found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check that 'Remenber me' checkbox is available or not | Remember me Error |  | Failed
38 |  | Functional Testing |  | Verifying that user will be able to login with the correct credentials | Should allow user to login | Found as per expectation | Phone number: 01813816794 Password: a1s2d3f4 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Try to login with correct credentials |  |  | Passed
39 |  |  |  | Verifying that the error message should display after entering the wrong credentials | Shouldn't allow user to login | Found as per expectation | Phone number: 01817509356 Password: in6rfdh | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Try to login with wrong credentials |  |  | Passed
40 |  |  |  | Verifying that user will get into their dashboard screen after login | A dashboard should be appeared after login | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Login with correct credentials |  |  | Passed
41 |  |  |  | Verifying that the password entered should be in encrypted form | Should be in encrypted form | Found as per expectation | a1s2d3f4 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Input password |  |  | Passed
42 |  |  |  | Verifying that logged in user should not logout on closing the browser | Shouldn't logout the user | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Login with correct credentials 4. Close the browser and reopen |  |  | Passed
43 |  |  |  | Verifying that logged in user doesn’t logout by clicking the back button on the browsers tab | Shouldn't logout the user | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Login with correct credentials 4. Click back button on the browsers tab |  |  | Passed
44 |  |  |  | Verifying that when logged-in user copy the URL and paste it into a different browser window, it redirects to login page | Should redirect to login page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Login with correct credentials 4. Copy the URL and paste it in different browser |  |  | Passed
45 |  |  |  | Verifying that Register and Login are not displaying when the user is logged in | Should display profile and logout | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Login with correct credentials |  |  | Passed
46 |  |  |  | Verifying that whether 'forget password' and 'create account' links are available on login page and working properly | 'forget password' and 'create account' links should be available and should work properly | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner |  |  | Passed
47 |  | Usability Testing |  | Verifying copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | 01813816794 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Copy and paste 01813816794 in phone number field |  |  | Passed
48 |  |  |  | Verifying keyboard tab button functionality | Should switch to another field | Functioning successfully | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click tab in every field |  |  | Passed
49 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click enter in every field |  |  | Passed
50 |  | Functional Testing | Logout | Verifying that user is successfully logged out and redirected to the Homepage | Should redirect to Homepage after logging out successfully | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Logout button at the right corner |  |  | Passed
51 |  |  |  | Verifying that all user session data is cleared after logging out | Should clear user session data | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Logout button at the right corner 3. Check user session data is cleared or not |  |  | Passed
52 |  |  |  | Verifying that notifications or background processes associated with user are stopped after logging out | Should stop notification or background processes associated with user | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Logout button at the right corner 3. Check notifications or background processes associated with user is showing or not |  |  | Passed
53 |  |  |  | Verifying that logging out from one device affects the login status on other devices for same account | Shouldn't affect login status of other device | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Logout button at the right corner 3. Check whether it affects the login status of other device |  |  | Passed
54 |  | UI Tesing | Forget Password | Verifying that forget password link is present on login page | Forget password link should be present in login page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check whether forget password link is present or not |  |  | Passed
55 |  |  |  | Verifying that forget password page should open by clicking forget password link | Should open forget password link | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click forget password link |  |  | Passed
56 |  |  |  | Verifying that email/phone number field is present to recover password | email/phone number field should be present | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click forget password link 4. Check whether email/phone number field is present |  |  | Passed
57 |  | Functional Testing |  | Verifying that confirmation message is showed after clicking on 'continue' by entering registered email/phone number | Should show a confirmation message | Found as per expectation | rahmantanjina983@gmail.com | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click forget password link 4. Enter registered email/phone number and click on 'continue' |  |  | Passed
58 |  |  |  | Verifying that user will get email/message with a password after entering registered email/phone number | Should get email/message with a password | Found as per expectation | rahmantanjina983@gmail.com | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click forget password link 4. Enter registered email/phone number and click on 'continue' |  |  | Passed
59 |  |  |  | Verifying that error message is showed for unregistered email/phone number | Should show a error message | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Click forget password link 4. Enter unregistered email/phone number and click on 'continue' |  |  | Passed
60 |  |  |  | Verifying that user should logged out from all browser and devices after updating password | Should logged out from all browser and devices | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check all browser and devices where account was logged in |  |  | Passed
61 |  |  |  | Verifying that user should be login successfully with the new password | Should allow user to login | Found as per expectation | 52758410 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Lonin with updated password |  |  | Passed
62 |  |  |  | Verifying that previous password is not working | Shouldn't allow user to login | Found as per expectation | a1s2d3f4 | 1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Login with previous password |  |  | Passed
63 | Homepage | UI Tesing | Header | Verifying that header section is aligned | Should be aligned | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether header is aligned or not |  |  | Passed
64 |  |  |  | Verifying that same header used on whole website pages | Header should be same on whole website | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether header is same or not on whole website |  |  | Passed
65 |  |  |  | Verifying that header is sticky on the whole page | Header should be sticky on whole page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether header is sticky or not on whole page |  |  | Passed
66 |  |  |  | Verifying that header and body section is distinguished | Should be distinguished | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether header and body are distinguished or not |  |  | Passed
67 |  |  |  | Verifying that the logo of the website added on the header is aligned | Should be aligned | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether logo is aligned or not |  |  | Passed
68 |  |  |  | Verifying that icons are aligned with the text | Should be aligned with text | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether icons are aligned or not with text |  |  | Passed
69 |  |  |  | Verifying that icon color is changing on mouse hover | Should change color on mouse hover | Not found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether icons change color on mouse hover | Mouse hover Error |  | Failed
70 |  |  |  | Verifying that search bar is added to the header | Search bar should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether serarch bar is added or not |  |  | Passed
71 |  |  |  | Verifying that dropdown options are added to the header | Dropdown should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether dropdown options are added or not |  |  | Passed
72 |  |  |  | Verifying that homepage is opened by clicking on the logo on all pages | Homepage should be open by clicking on logo | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether homepage is opend by clicking on logo |  |  | Passed
73 |  |  |  | Verifying whether all links are opening on correct page | All links should open on correct page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether all links of header are opening on correct page or not |  |  | Passed
74 |  | UI Tesing | Footer | Verifying that footer section is aligned at the end of the page | Should be aligned at the end of the page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether footer is aligned at the end of the page |  |  | Passed
75 |  |  |  | Verifying that there is no extra white space at the end of the footer on high screen resolutions | Should be no extra white space at the end | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether there is no extra white space at the end of the footer |  |  | Passed
76 |  |  |  | Verifying that footer section is the same for whole website | Should be same for whole website | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether footer section is same or not for whole website |  |  | Passed
77 |  |  |  | Verifying that there is no spelling mistakes on the footer section | Mistakes in grammar or spelling shouldn't be found | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether there is any spelling mistake or not |  |  | Passed
78 |  |  |  | Verifying that all social links with icons added on the footer | All social links should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether all social links with icons are added or not on footer |  |  | Passed
79 |  |  |  | Verifying that all links and icons color are changing on mouse hover | Should change color on mouse hover | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether all links and icons of footer are changing color on mouse hover |  |  | Passed
80 |  |  |  | Verifying that there is equal space for elements links, button, and social links from top and bottom | Space for elements links, button, and social links from top and bottom should be equal | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether space for elements links, button, and social links from top and bottom is equal |  |  | Passed
81 |  |  |  | Verifying whether all links are opening on correct page | All links should open on correct page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether all links of footer are opening on correct page or not |  |  | Passed
82 |  |  |  | Verifying whether correct year is added to the footer section | Correct year should be added on footer section | Not found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether correct year is added or not on footer | Incorrect year Error |  | Failed
83 |  |  |  | Verifying whether the copyright section is added to the footer | Copyright section should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether copyright section is added or not on footer |  |  | Passed
84 |  |  |  | Verifying whether the copyright icon is added or not on the footer section | Copyright icon should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether copyright icon is added or not on footer |  |  | Passed
85 |  |  |  | Verifying whether contact information are added or not | Contact information should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether contact information are added or not on footer |  |  | Passed
86 |  |  |  | Verifying whether app downloading are added or not | App downloading option should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether app downloading options are added or not on footer |  |  | Passed
87 |  | UI Tesing | Search Bar | Verifying that search field is present and aligned | Search bar should be present and aligned | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether search bar is present and aligned or not |  |  | Passed
88 |  |  |  | Verifying whether placeholder text is added on search or not | Placeholder text should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether placeholder text is added or not |  |  | Passed
89 |  |  |  | Verifying that spelling and grammar is correct for placeholder text | Spelling and grammar should be correct | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether spelling and grammar of placeholder text is correct or not |  |  | Passed
90 |  |  |  | Verifying that search icon is added on the field | Search icon should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether seach icon is added or not |  |  | Passed
91 |  |  |  | Verifying that cursor is present on click on the search icon | Cursor should be present on click | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether cursor is present on click or not |  |  | Passed
92 |  | Functional Tesing |  | Verifying that search is functional and generating the correct result for correct keywords or not by adding a valid search | Should be functional and should generate correct result | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether search bar is functional and generating correct result |  |  | Passed
93 |  |  |  | Verifying that search is working by adding keywords and pressing the Enter key on keyboard | Should work by adding keywords and pressing enter | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether working or not by adding key words and pressing enter |  |  | Passed
94 |  |  |  | Verifying that search is working by adding keywords and on click on search button | Should work by adding keywords and clicking search button | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether working or not by adding key words and clicking search button |  |  | Passed
95 |  |  |  | Verifying that an error message is displayed for entering invalid keywords | An error message should be displayed | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether error message is displayed or not for entering invalid keywords |  |  | Passed
96 |  |  |  | Verifying that an error message is displayed for blank input | An error message should be displayed | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether error message is displayed or not for entering blank input |  |  | Passed
97 |  |  |  | Verifying that search result generated is in correct order as per requirement | Result should be generated in correct order | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether generated search result is in correct order or not |  |  | Passed
98 |  |  |  | Verifying that pagination added in case the search result goes on the number of pages | Pagination should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether pagination is added or not |  |  | Passed
99 |  |  |  | Verifying whether pagination is accessible or not by clicking on Next, Previous and number | Pagination should be accessible by clicking Next, Previous and number | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether pagination is accessible or not by clicking Next, Previous and number |  |  | Passed
100 |  |  |  | Verifying whether suggestions are shown or not on adding a keyword to the search | Suggestion should be shown | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether suggestion is shown or not |  |  | Passed
101 |  |  |  | Verify whether related keywords are added to the search result or not | Related keywords should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether relater keywords are added or not |  |  | Passed
102 |  | UI Tesing | Menu Bar | Verifying whether label text of menu bar is as per requirements and aligned or not | Label text of menu bar should be as per requirement | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether label text are as per requirement or not |  |  | Passed
103 |  |  |  | Verifying that order of the values in the menu bar is as per the requirement | Values of menu bar should be as per requirement | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether values of menu bar are as per requirement or not |  |  | Passed
104 |  |  |  | Verifying that default selected value is shown on the menu bar | Default selected value should be shown | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether default selected values are or not |  |  | Passed
105 |  |  |  | Verifying that there is no blank value shown in the menu bar list | No blank values should be shown | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether any blank values are shown or not in menu bar list |  |  | Passed
106 |  |  |  | Verifying that spelling of the values in the menu bar list is correct | Spelling of values in menu bar list should be correct | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether spelling of menu bar values are correct or not |  |  | Passed
107 |  |  |  | Verifying whether all the values in the menu bar list align or not | Values of menu bar should be aligned | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether menu bar values are aligned or not |  |  | Passed
108 |  |  |  | Verifying whether proper spacing is added on the menu bar values or not | Proper spacing should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether proper spacing are added or not in menu bar list |  |  | Passed
109 |  |  |  | Verifying whether on mouse hover mouse pointer change from a pointer to hand or not | On mouse hover mouse pointer should be changed from a pointer to hand | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether mouse pointer is changed or not from a pointer to hand on mouse hover |  |  | Passed
110 |  |  |  | Verifying whether mouse hover effect is added to the menu bar list or not | Color should be changed on mouse hover | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether color is changed or not on mouse hover |  |  | Passed
111 |  | Functional Tesing |  | Verifying that all menu bar values are clickable | All menu bar values should be clickable | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether all menu bar values are clickable or not |  |  | Passed
112 |  |  |  | Verifying whether scroll-down functionality working in the menu bar list or not | Scroll-down functionality should be working properly | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether scroll-down functionality is working properly or not |  |  | Passed
113 |  |  |  | Verifying that by clicking on a collapsed menu bar value then sub-menu values are expanded | Sub-menu values should be expended by clicking on collapsed menu bar value | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether sub-menu values are expended or not by clicking on collapsed menu bar value |  |  | Passed
114 |  |  |  | Verifying that by clicking on menu bar value it navigates to the destination page | By clicking on menu bar value it should navigate to the destination page | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether by clicking on menu bar value it navigates to the destination page or not |  |  | Passed
115 | Add to Cart | UI Tesing | Add to Cart button | Verifying that Add to Cart button is present | Add to cart button should be present | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether Add to Cart button is presents on products or not |  |  | Passed
116 |  |  |  | Verifying that button text is related to the functionality | Button text should be related to functionality | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether button text of Add to Cart button is related to the functionality or not |  |  | Passed
117 |  |  |  | Verifying that cart icon is added on the button | Cart icon should be added | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether cart icon is added in Add to Cart button or not |  |  | Passed
118 |  |  |  | Verifying that color, height and width of the button are as per requirement | Color, height and width should be as per requirement | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether color, height and width of Add to Cart button are as per requirement or not |  |  | Passed
119 |  |  |  | Verifying that colour of the button changed on the mouse hover | Color should be changed on the mouse hover | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether Add to Cart button change color on mouse hover or not |  |  | Passed
120 |  | Functional Tesing |  | Verifying that Add to Cart button is clickable | Button should be clickable | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether Add to Cart button is clickable or not |  |  | Passed
121 |  |  |  | Verifying that user is able to add items in cart | User should be able to items in cart | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether user is able to add items to cart or not |  |  | Passed
122 |  |  |  | Verifying that count of cart getting increase or not when user click Add to Cart button of an item | Count of cart should increase by clicking Add to Cart button | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether count of cart is increasing or not by clicking Add to Cart button |  |  | Passed
123 |  |  |  | Verifying that confirmation message is displayed when user add an item successfully | Confirmation message should be displayed when user add an item successfully | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether confirmation message is displayed or not when user add an item successfully |  |  | Passed
124 |  |  |  | Verifying that both count of cart and item increases when user click Add to Cart button multiple times for same item | Count of cart and item should increase by clicking Add to Cart button multiple time for same item | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether count of cart and item is increasing by clicking Add to Cart button multiple time for same item |  |  | Passed
125 |  |  |  | Verifying whether user is able to add an item to cart which is out of stock | Shouldn't allow user to add an item to cart which is out of stock | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether user is able to add an item to cart which is out of stock |  |  | Passed
126 | Shopping Cart | UI Tesing | Shopping Cart | Verifying whether Shopping Cart is present or not | Shopping Cart should be present | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether Shopping Cart is present or not |  |  | Passed
127 |  |  |  | Verifying that design, color and font are as per requirement | Design, color and font are as per requirement | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether design, color and fonts are as per requirment or not |  |  | Passed
128 |  | Functional Tesing |  | Verifying that cart is empty when no item is add in the cart | Cart should be empty when no item is add | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether cart is empty when no item is added |  |  | Passed
129 |  |  |  | Verifying that count of cart getting increase when user adds an item to the cart | Count of cart should increase when user adds an item | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether count of cart is increasing when user adds an item |  |  | Passed
130 |  |  |  | Verifying that count of cart getting increase when user adds multiple items to the cart | Count of cart should increase when user adds multiple items | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether count of cart is increasing when user add multiple items |  |  | Passed
131 |  |  |  | Verifying that both count of cart and item in cart increase when user adds same item multiple times | Count of cart and item should increase when user add same item multiple times | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether count of cart and item is increasing when user adds an item multiple times |  |  | Passed
132 |  |  |  | Verifying that count of cart getting decrease or not when user deletes an item to the cart | Count of cart should decrease when user deletes an item | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether count of cart is decreasing when user deletes an item |  |  | Passed
133 |  |  |  | Verifying that cart shows empty or not when user deletes all items to the cart | shows empty cart when user deletes all items | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether cart is empty when user deletes all items from cart |  |  | Passed
134 |  |  |  | Verifying that cart is showing the correct price of items | Cart should show the correct price of items | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether cart is showing the correct price of items |  |  | Passed
135 |  |  |  | Verifying that cart is showing the correct total amount of price | Cart should show the correct total amount of price | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether cart is showing the correct total amount of price |  |  | Passed
136 |  |  |  | Verifying that tolal amount of price is increasing when user adds a new item | Total amount of price should increase when user adds a new item | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether the total amount of price is increasing when user add a new item |  |  | Passed
137 |  |  |  | Verifying that tolal amount of price is decreasing when user deletes an item | Total amount of price should decrease when user deletes an item | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether the total amount of price is decreasing when user deletes an item |  |  | Passed
138 |  |  |  | Verifying that cart is showing discounted price when user enters a valid promo code | Discounted price should be shown by entering valid promo code | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether discounted price is showing by entering valid promo code |  |  | Passed
139 |  |  |  | Verifying that cart is showing an error message when user enters a invalid promo code | Error message should be shown by entering invalid promo code | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether error message is showing by entering invalid promo code |  |  | Passed
140 |  |  |  | Verifying whether the quantity of an item can be increased and decreased in cart | Allow user to increase or decrease the quantity of an item in cart | Not found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Add a item in shopping cart 3. Try to increase or decrease the quantity of that item in cart | Cart quantity Error |  | Failed
141 |  |  |  | Verifying that user is redirected to the checkout page after clicking on the checkout button | Redirect user to checkout page by clicking checkout button | Found as per expectation | N/A | 1. Visit the URL https://www.startech.com.bd/ 2. Check whether redirect user to checkout page by clicking checkout button |  |  | Passed
|  |  | Improvement Scope | Password field should be more secure and stronger
In Forget Password section password update link shoud be sent instead of sending password directly
"Remember me" checkbox should be added in Login section

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Startech bd LTD
Module Name | User Management, Homepage, Add to Cart & Shopping Cart |  |  |  |  | Total No. | Status
Feature Name | Register, Login, Logout, Forget Password, Header, Footer, Search Bar, Menu Bar, Add to Cart & Shopping Cart
Test Case Version | 1 |  |  |  |  | 133 | PASS
Written By | Tanjina Rahman |  |  |  |  | 8 | FAIL
Executed By | Tanjina Rahman |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment : Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 133 | 8 | 0 | 0 | 141
Grand Total | 133 | 8 | 0 | 0 | 141
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Accept numeric value as firstname and lastname.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input numeric value in firstname and lastname field
Env: Production.
Module: Register
Priority: Medium
Severity: Minor
Screenshot: Numeric value error
Expected: Should not allow registration with firstname and lastname as numeric value.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 02
Issue: Accept special character as firstname and lastname.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input special character in firstname and lastname field
Env: Production.
Module: Register
Priority: Medium
Severity: Minor
Screenshot: Special character error
Expected: Should not allow registration with firstname and lastname as special characters.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 03
Issue: Registered with invalid email address.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Click on Register button at the right corner 3. Input a invalid email in email field
Env: Production.
Module: Register
Priority: High
Severity: Major
Screenshot: Invalid email error
Expected: Should not allow registration with invalid email address.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 04
Issue: Eye icon missing on password field.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check that eye icon is available or not in password field
Env: Production.
Module: Login
Priority: Low
Severity: Minor
Screenshot: Eye icon error
Expected: Eye icon should be present in password field.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 05
Issue: Remember me checkbox is missing.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Click on Login button at the right corner 3. Check that 'Remenber me' checkbox is available or not
Env: Production.
Module: Login
Priority: Medium
Severity: Minor
Screenshot: Remember me error
Expected: Remember me checkbox should be present in Login page.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 06
Issue: Mouse hovering issue on header.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Check whether icons on header section change color on mouse hover
Env: Production.
Module: Homepage
Priority: Low
Severity: Minor
Screenshot: Hovering error
Expected: Icons should change color on mouse hover.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 07
Issue: Incorrect year on footer section.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Check whether correct year is added or not on footer
Env: Production.
Module: Homepage
Priority: Low
Severity: Minor
Screenshot: Incorrect year error
Expected: Correct year should be added in footer section.
Responsible QA: Tanjina Rahman
Bug Reporting
# SL 08
Issue: Feature of increasing or decreasing quantity of an item in cart is missing.
Reproducing Steps:
1. Visit the URL https://www.startech.com.bd/ 2. Add a item in shopping cart 3. Try to increase or decrease the quantity of that item in cart
Env: Production.
Module: Shopping Cart
Priority: High
Severity: Major
Screenshot: Quantity error
Expected: Should allow to increase or decrease quantity of an item in cart.
Responsible QA: Tanjina Rahman

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (141/141)*100 = 100%
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/141)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (133/141)*100 = 94.3%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (8/141)*100 = 5.7%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/141)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A